## Sheet1
SIPC - Current Tasks, Plans & Status - 4th July 2024
# | Description | Person Responsible | Accounts Code | Accounts Description | Type | Frequency | Status (Updated 11th July 2024) | Priority | Annual Cost £ (exc VAT)
1 | Complete installation of path & dome base in CV playgound | Clerk Playsafe Playgrounds | GM11 | Parish Improvement | Project | One-off | Agreed quote for installation due before year end | 1 | 4659
2 | Complete re-furbishment of area around Stedham Telephone Box | Clerk | GM11 | Parish Improvement | Project | One-off | Awaiting second quote First quote (+£1350 for tarmac over concrete) | 2 | 2888
3 | Check AED condition Update National Defibrillator Website | AH | GM09 | General Parish Maintenance | Housekeeping | Monthly | Ongoing AH now contact for The Circuit Replacement Pads | N/A | 180
4 | Refurbishment of Iping Telepohne Box | Clerk | GM11 | Parish Improvement | Project | One-off | Contractor not able to do until 2025 (Quote July 2023) | 3 | 3525
5 | Installation of AED & Cabinet in Iping Telephone Box |  | GM12 | Parish Improvement | Project | One-off | Plan to tidy/clean-up and install AED/Cabinet before refurbishment carried out. AED/Cabinet cost (approx) | 1 | 1500
6 | Replacement of lettering on Stedham Signpost | Clerk | GM11 | Parish Improvement | Project | One-off | Replace plastic lettring with routed letters. Quote from Playsafe for routing letters accepted (waiting schedule) | 1 | 643
7 | Traffic Regulation Order (TRO) | TS | ?? | ?? - possibly new code | Project | One-off | 2 x TROs for Stedham & Iping - cost unknown Drop down priority | 3
8 | Litter Picking | Clerk | GM09 | General Parish Maintenance | Housekeeping | 2 / year | March & November Include general housekeeping tasks | N/A | 40
9 | Afternoon Tea Club | TS | COMMS07 | Tea Club | Project | 3 / Year | March, September & December September 2024 cancelled £5 fee per person | N/A | 600
10 | Newsletter | HB | COMMS03 | Communications | Project | 3 / Year | Usually March, July & November July cancelled for 2024 Next publication October 2024 | N/A | 1172
11 | Wild Flower | RC | GM07 | Wild Flower | Housekeeping | On-going | No current plans. Include in September to plan for bulk planting. | N/A | 200
12 | Website | Clerk |  |  | Housekeeping | On-going | Regular Updates |  | 0
13 | SIPC FaceBook | AH |  |  | Housekeeping | On-going | Regular Updates |  | 0
14 | Sussex Wildlife Trust | RC |  |  | PC Contact | On-going |  |  | 0
15 | Midhurst Area Cycling. | RW |  |  | PC Contact | On-going |  |  | 0
16 | Stedham Memorial Hall | RW |  |  | PC Contact | On-going | RW to ask for stand-in if not available |  | 0
17 | Stedham Primary School | AH |  |  | PC Contact |  |  |  | 0
18 | Stedham Sports Association | None | [6 empty] | 0
19 | Parish Online | TS |  |  | Housekeeping |  |  |  | 37.5
20 | Cross/All Parishes Working Group | Clerk, Chair |  |  | Housekeeping |  |  |  | 0
21 | Sussex Police - Neighbourhood Policing | AH |  |  | Housekeeping | Bi-monthly | AH to ask for stand-in if not available |  | 0
22 | Salt Bins - check content | Clerk |  |  | Housekeeping |  |  |  | 0
23 | Parish Risk Assessment | Clerk |  |  | Housekeeping |  |  |  | 0
24 | START | AH |  |  | PC Contact |  | AH to ask for stand-in if not available |  | 0
25 |  | Clerk |  |  | Housekeeping |  |  |  | 0
26 |  | Clerk |  |  | Housekeeping |  |  |  | 0
27 |  | Clerk |  |  | Housekeeping |  |  |  | 0